## Product Backlog
| Story Points | Sprint | Stakeholder | Wants to... | So that... | So that...
1 | 5 | 1 | User | View information about the charity and race |  | They understand the events purpose and goals
2 | 5 | 1 | User | View race date, time, and location |  | They know when and where the race takes place
3 | 8 | 1 | User | Access the site on mobile, tablet, and desktop |  | They can use the site on any device with good user experience.
4 | 5 | 1 | User | View the route and layout of the race |  | They know where they are going and the boundaries of the race
5 | 8 | 2 | User | Register for the 5k with name, email, age, emergency contact and password |  | They can be prepared to participate in the race
6 | 5 | 2 | User | Log in securely to their account |  | They can access exclusive race information
7 | 3 | 2 | User | Receive error messages for incorrect login or missing registration fields |  | They understand what needs to be corrected
8 | 5 | 2 | User | create or join a team by entering a team name |  | They can run as a group with family and friends
9 | 5 | 3 | User | View race-day schedule |  | They know event timing and check in times
10 | 5 | 3 | User | View teammates |  | So they can plan together for the race
11 | 5 | 3 | User | View addition race instructions and rules |  | To further prepare for race day
12 | 8 | 4 | Client administrator | View a table of all registered runners |  | They can manage participation
13 | 5 | 4 | Client administrator | Promote a registered user to admin |  | Responsibilities can be shared
14 | 3 | 4 | Developer | Automatically make the first registered user an admin |  | The system has an initial administration
15 | 8 | 5 | Advertiser | Send email reminders about race day |  | To keep people informed
16 | 5 | 5 | Configuration Manager | Configure email reminder timing |  | Notifications are sent at appropriate intervals to prevent spamming or info being hidden
17
18
Past stories
| 5 | 1 | Developer | Get all development tools working on local machine |  | The team can begin development
| 5 | 1 | Configuration Manager | Identify hosting and deployment infrastructure | the code can run | The application can be deployed
| 3 | 1 | Developer | Set up project repository in Github |  | Code can be version controlled
| 3 | 1 | Developer | Create initial project structure any folders layout etc |  | The team has a clean development foundation
| 5 | 1 | Developer | Configure database connection locally |  | Data can be stored and tested
| 3 | 1 | Configuration Manager | Define environment configuration settings |  | The apps runs consistently across environments
| 2 | 1 | Developer | Install and configure UI framework |  | Responsive design can be implemented efficiently
| 2 | 1 | Configuration Manager | Create deployment checklist |  | Production deployment is controlled and repeatable

## Sprint Backlog (weeks 1-2)
Sprint's Goal: "Public Website, Registration, and Basic Login System" | [5 empty] | Start Date: | 2026-02-16 | Work Done per day per task [Hours]
User Story | Time (est) | Time (spent) | Time (left) | Task | Time (est) | Who's working | Status | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01
| 0 | 0 | 0
View Charity and Race Information | 13 | 14 | 0 | Create homepage layout | 3 | Daniel Howard | Done |  | 1 |  |  | 1 |  |  |  |  | 1
|  |  |  | Add charity mission section on the UI | 2 | Bryce Batey | Done |  |  | 1 | [5 empty] | 1
|  |  |  | Add race date/location information section | 3 | Ponpawit Potisom | Done | 1 |  |  | 1 | [6 empty] | 1
|  |  |  | add navigation bar | 3 | Bryce Batey | Done |  |  | 1 | 1 |  |  |  |  | 1
|  |  |  | Finish last touch up for homepage | 2 | Daniel Howard | Done |  | 1 | [7 empty] | 2
|  |  |  | - | 0 | Ponpawit Potisom | Done
User Register for 5K | 9 | 9 | 0 | Design registration page UI | 2 | Daniel Howard | Done |  |  | 2
|  |  |  | Add required fields (basic info) | 4 | Bryce Batey | Done |  |  | 1 | [5 empty] | 2 |  |  | 1
|  |  |  | Create database user table | 3 | Ponpawit Potisom | Done |  | 1 |  |  | 1 |  |  |  |  | 1
Login System / Display logiin errors | 21 | 22 | 0 | Create login page UI | 6 | Ponpawit Potisom | Done | 1 |  | 1 |  | 1 |  |  |  | 1 |  | 1 | 1
|  |  |  | Implement login logic + logout feature | 5 | Daniel Howard | Done |  | 1 |  | 2 |  |  |  |  | 2 |  | 1
|  |  |  | Implement session management | 5 | Bryce Batey | Done |  |  | 1 |  |  |  |  | 2 |  | 1 |  | 1
|  |  |  | registration vaildation messages + login error messages | 5 | Ponpawit Potisom | Done | 1 |  |  | 1 |  |  |  |  | 2 |  |  | 1
TOTAL | 43 | 45 | 0 |  |  |  |  | 3 | 4 | 7 | 5 | 3 | 0 | 0 | 2 | 9 | 5 | 3 | 4 | 0 | 0
Daily burnout | 43 | 100% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total time left (from estimate) | [5 empty] | Estimate | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43
Total time left (from spent) | [5 empty] | Burnout | 45 | 42 | 38 | 31 | 26 | 23 | 23 | 23 | 21 | 12 | 7 | 4 | 0 | 0 | 0
Complexity (story points) | 31

## Sprint Backlog (weeks 3-4)
Sprint's Goal: "User Registration, Login, and Dashboard System" | [5 empty] | Start Date: | 2026-03-02 | Work Done per day per task [Hours]
User Story | Time (est) | Time (spent) | Time (left) | Task | Time (est) | Who's working | Status | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15
| 0 | 0 | 0
User Registration | 16 | 20 | 0 | Design registration page UI | 3 | Daniel Howard | Done | 1 |  |  |  | 1 |  |  |  | 1 |  |  | 1
|  |  |  | Add input fields (name, email, age) | 3 | Bryce Batey | Done |  |  | 1 |  |  |  |  | 1 |  |  | 1
|  |  |  | Add password + team field | 2 | Ponpawit Potisom | Done |  |  |  | 1 |  |  |  |  | 1
|  |  |  | Add form validation | 4 | Daniel Howard | Done |  | 2 | [5 empty] | 1 |  |  | 2
|  |  |  | Prevent duplicate email | 2 | Bryce Batey | Done |  |  | 1 | [6 empty] | 1 |  | 1
|  |  |  | Store user data | 2 | Ponpawit Potisom | Done | 1 | [6 empty] | 1 |  |  | 1
Login System | 11 | 11 | 0 | Create login page UI | 3 | Ponpawit Potisom | Done |  | 1 |  |  | 1 |  |  |  |  | 1
|  |  |  | Implement login authentication | 5 | Bryce Batey | Done |  |  | 1 |  | 2 |  |  |  | 1 |  | 1
|  |  |  | Add error handling (wrong password) | 3 | Daniel Howard | Done |  | 1 |  |  | 1 |  |  | 1
Basic Navigation | 11 | 11 | 0 | Build navigation bar | 3 | Daniel Howard | Done |  |  | 1 | [6 empty] | 1
|  |  |  | Link pages (Home, Login, Register) | 3 | Bryce Batey | Done |  |  |  | 1 |  |  |  | 1 |  |  |  | 1
|  |  |  | Add button navigation logic | 2 | Daniel Howard | Done |  | 1 | [6 empty] | 1
|  |  |  | Add logout functionality | 3 | Ponpawit Potisom | Done |  |  | 1 |  |  |  |  | 2 |  |  | 1
TOTAL | 38 | 42 | 0 |  |  |  |  | 2 | 5 | 5 | 2 | 5 | 0 | 0 | 7 | 4 | 3 | 6 | 3 | 0 | 0
Daily burnout | 38 | 100% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total time left (from estimate) | [5 empty] | Estimate | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38
Total time left (from spent) | [5 empty] | Burnout | 42 | 40 | 35 | 30 | 28 | 23 | 23 | 23 | 16 | 12 | 9 | 3 | 0 | 0 | 0
Complexity (story points) | 31

## Sprint Backlog (weeks 5-6)
Sprint's Goal: Build user dashboard + admin page and display personalized data | [5 empty] | Start Date: | 2026-03-16 | Work Done per day per task [Hours]
User Story | Time (est) | Time (spent) | Time (left) | Task | Time (est) | Who's working | Status | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29
| 0 | 0 | 0
Dashboard Page | 21 | 22 | 0 | Create dashboard layout | 4 | Daniel Howard | Done |  | 1 |  | 1 |  |  |  |  | 1 |  |  | 1
|  |  |  | Display user info | 4 | Bryce Batey | Done | 2 |  | 1 |  | 1
|  |  |  | Show team members | 4 | Ponpawit Potisom | Done |  | 1 |  |  | 1 |  |  |  |  | 1 |  | 1
|  |  |  | Add checklist section | 4 | Daniel Howard | Done |  |  | 1 |  | 2 |  |  |  | 2
|  |  |  | Display race schedule | 4 | Bryce Batey | Done | 1 |  |  | 1 | [5 empty] | 1 |  | 1
|  |  |  | Double check if it works | 1 | Ponpawit Potisom | Done |  | 1
Data Integration | 6 | 6 | 0 | Load user data after login | 2 | Ponpawit Potisom | Done |  |  | 2
|  |  |  | Connect dashboard to stored data | 2 | Bryce Batey | Done |  | 1 | [6 empty] | 1
|  |  |  | Update UI dynamically | 2 | Daniel Howard | Done |  |  |  | 1 | [6 empty] | 1
Admin Panel | 10 | 10 | 0 | Create admin page UI | 3 | Daniel Howard | Done |  |  | 1 |  |  |  |  | 1 |  | 1
|  |  |  | Build basic users table | 3 | Bryce Batey | Done | 1 |  |  |  | 1 | [6 empty] | 1
|  |  |  | Improve table layout | 2 | Daniel Howard | Done |  |  | 1 | [5 empty] | 1
|  |  |  | Display user data (name, email, age, team) | 2 | Ponpawit Potisom | Done | [11 empty] | 2
TOTAL | 37 | 38 | 0 |  |  |  |  | 4 | 4 | 6 | 3 | 5 | 0 | 0 | 1 | 5 | 3 | 1 | 6 | 0 | 0
Daily burnout | 37 | 100% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total time left (from estimate) | [5 empty] | Estimate | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37
Total time left (from spent) | [5 empty] | Burnout | 38 | 34 | 30 | 24 | 21 | 16 | 16 | 16 | 15 | 10 | 7 | 6 | 0 | 0 | 0
Complexity (story points) | 31

## Sprint Backlog (weeks 7-8)
Sprint's Goal: Build backend system and improve login security + overall project | [5 empty] | Start Date: | 2026-03-30 | Work Done per day per task [Hours]
User Story | Time (est) | Time (spent) | Time (left) | Task | Time (est) | Who's working | Status | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12
| 0 | 0 | 0
Backend Integration | 14 | 14 | 11 | Set up basic backend (server) | 3 | Daniel Howard | TODO | 1
|  |  |  | Connect frontend to backend | 2 | Bryce Batey | TODO
|  |  |  | Create user database table | 2 | Ponpawit Potisom | TODO | 1
|  |  |  | Save user registration data | 3 | Daniel Howard | TODO
|  |  |  | Load user data for dashboard | 2 | Bryce Batey | TODO | 1
|  |  |  | Test backend connection and fix bugs | 2 | Ponpawit Potisom | TODO
Secure Login System | 9 | 9 | 9 | Improve login authentication logic | 2 | Ponpawit Potisom | TODO
|  |  |  | Show error messages for wrong login | 4 | Bryce Batey | TODO
|  |  |  | Protect admin access | 3 | Daniel Howard | TODO
Admin Panel Improvements | 10 | 10 | 10 | Connect admin panel to backend | 3 | Daniel Howard | TODO
|  |  |  | Add search users feature | 3 | Bryce Batey | TODO
|  |  |  | Add edit user option | 2 | Daniel Howard | TODO
|  |  |  | Improve table performance | 2 | Ponpawit Potisom | TODO
TOTAL | 33 | 33 | 30 |  |  |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Daily burnout | 33 | 100% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total time left (from estimate) | [5 empty] | Estimate | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33
Total time left (from spent) | [5 empty] | Burnout | 33 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
Complexity (story points) | 31

## Sprint Backlog (weeks 9-10)
Sprint's Goal: Improve backend, make login more secure, and fix UI issues | [5 empty] | Start Date: | 2026-04-13 | Work Done per day per task [Hours]
User Story | Time (est) | Time (spent) | Time (left) | Task | Time (est) | Who's working | Status | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26
| 0 | 0 | 0
Backend Improvements | 16 | 16 | 16 | Improve database structure | 3 | Daniel Howard | TODO
|  |  |  | Optimize data loading | 3 | Bryce Batey | TODO
|  |  |  | Improve backend routes | 3 | Ponpawit Potisom | TODO
|  |  |  | Fix backend bugs | 2 | Daniel Howard | TODO
|  |  |  | Test backend performance | 3 | Bryce Batey | TODO
|  |  |  | Add color styling to improve UI design | 2 | Ponpawit Potisom | TODO
Security Improvements | 7 | 7 | 7 | Improve password security | 2 | Ponpawit Potisom | TODO
|  |  |  | Improve login | 3 | Bryce Batey | TODO
|  |  |  | Test login system | 2 | Daniel Howard | TODO
UI & UX Improvements | 11 | 11 | 11 | Improve navigation flow | 3 | Daniel Howard | TODO
|  |  |  | Improve button and form design | 3 | Bryce Batey | TODO
|  |  |  | Make pages more consistent | 3 | Daniel Howard | TODO
|  |  |  | Test user experience | 2 | Ponpawit Potisom | TODO
TOTAL | 34 | 34 | 34 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Daily burnout | 34 | 100% | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total time left (from estimate) | [5 empty] | Estimate | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34
Total time left (from spent) | [5 empty] | Burnout | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34
Complexity (story points) | 31

## Team members
Name | How often we meet | Roal | How we meet
Daniel Howard | 1 time per week | Scum Leader | In-person
Bryce Batey | 1 time per week | Developer | Discord
Ponpawit Potisom | 1 time per week | Developer | In-person

## Task statuses
TODO
Working
Done
Blocked
Verify

## Stakeholders
User
Moderator
Client administrator
Advertiser
Developer
Configuration Manager